## BugSheet
S.No. |  | Bugs Identified | Module |  | resources | BYS Status | Developer Remarks | Kowtha Status | Kowtha Remarks
aditya birla
1 | financial analysis | In the Financial Analysis section, I have entered the data, but there is no Save button available. | Web |  | Shanmuk | Fixed
2 | synopsis/ feedback | The Synopsis and Feedback have been given by the verifier executive, but in the Verifier login, the Synopsis/Feedback is not reflecting. | Backend
3 | verification executive web | While trying to log in, after entering the phone number and OTP and clicking the Submit button, an error message “Failed to fetch the attendance record” is displayed. | Web |  | Shanmuk | Completed
4 | verification executive web | When clicking on the User tab, an error message appears saying “Failed to fetch user.” | Web |  | Shanmuk | Completed
5 | user tab ifilter | in the filter role ther is verifier executive is not reflycting | Backend
6 | template name | I created the loan with the bank name as Aditya Birla and selected the template as Aditya Birla HL, but in the PDF, the HL is not reflecting. | Backend
7 | verification executive web | The Time of Visit is not reflecting on the Verify tab. | Web
8 | pdf | The Family Members Details are not reflecting in the PDF. | Backend |  |  | Completed
9 | pdf | In the PDF, the fields Field Visit Time, PD Verified By Officer, and PD Verified Date are not reflecting. | Backend
10 | photo capture | In the MSME Licence section, the Latitude/Longitude values are showing as NaN instead of the actual coordinates. | Backend
11 | financial analysis | The data is not reflecting in the exported Excel file. | Backend
12 | templete name edit | I have created the loan with the bank name Aditya Birla and selected the template Aditya Birla HL, but in the generated PDF, the “HL” is not reflecting. After generating the final PDF, it is generated successfully, but when I try to change the template name, it is still editable — it should not be editable after the final PDF is generated. | Backend |  |  | Fixed
13 | pdf navigation | I have created the loan with the bank name Aditya Birla and selected the template Aditya Birla HL, but in the generated PDF, the “HL” is not reflecting. After generating the final PDF, it is generated successfully, but the page is navigating to the Verify tab instead of staying on the current page. | Backend
| select template | In the Verify tab, the Select Template option needs to be hidden. | Web |  | Shanmuk | Fixed
| verify tab | required filters or search bar | Web |  | Shanmuk | Fixed
AMBIT
| templete name | In the PDF, the Template Name is reflecting twice (duplicate), and in some places, the alignment needs to be fixed. | Backend |  |  | Completed
| edit | When I edit anything in the Verify tab and click the Save button, two APIs are being called. | Web |  |  | Fixed
AXIS FINANCE
mobile | applicant asked to postpone | when im clicking to the applicant asked to postpone? field selecting no option there error message is reflucting as something went wrong | Mobile |  |  | fixed
AXIS FINANCE UBL ABOVE 10L
| pdf | The Loan Details, Bank Details, Family Details, and Shareholders sections are not reflecting in the PDF. | backend |  |  | fixed
|  | Car, Bike and any other vehicle (Company Name and Model) NA try is no feild to enter the data or edit | Web |  |  | fixed
AXIS FINANCE UBL below 10L
|  | The No. of Visits is not reflecting in the Verify tab. | Web
|  | visited by is not reflucting | Web
| verifytab |  | frontend
| pdf | loan details bank details family details shareholders and end user , aree not reflucting in the pdf | backend |  |  | fixed
|  | Car, Bike and any other vehicle (Company Name and Model) NA try is no feild to enter the data or edit | frontend |  |  | fixed
axis bank
| pdf | Banking performance Any cheque bounces seen (Y/N): /bank details/Years in current business NaN data is not reflucting in the pdf /family details need have table and some details are not refluting/ stock seen/ business activity seen/ | backend |  |  | Fixed
business financial profile-> no debit fielsd and no credit field text is refllucting
|  | synopsis giventhe data clicking save button error message is reflucting as Failed to submit synopsis | frontend
| pdf | In the Status of PD field, the Verifier Executive set it to Positive, and the Verify User changed it to Negative, but in the PDF, it is still showing as Positive. | backend
| pdf | ANNEXURE1: Income assessment for Asha Home Loans need to remove from pdf |  |  |  | Fixed
arka fincap
| verify tab | The Business Activity and Stock Level Observed at the Time of Visit" field should be a string but in the web it is showing as time picker | Web
axis agri
|  | mobile submition is not working |  |  |  | fixed
chola
|  | in the pdf ->asset/customers reference/other income/existing loans/banking details/comfort factor/discomfort / are not reflucting in the pdf |  |  |  | Fixed
DCB
| mobile submition is not working |  |  |  |  | fixed
hero fincorp
no of visit is not refluting in the web
about the applicant is details at\re not reflucting in the web
about the business is details at\re not reflucting in the web
i have given thedetails in the document observed feild but in the web the data is not refluting
existing loan
Security Offered data is not reflucting in the web
Other Business / Income data is not reflucting in the web
| pdf | Field Visit Time/ PD Verified By (Officer)/ PD Verified Date is not reflucting in the pdf
herohousing salaried
if im editing something in the web ther no save button in the web
if im uploarding the image with disable geotab in the pdf in the image lat NAN and long NAN
pd visit date is not reflucting in the web
pd visit time is not reflucting in the web
| Reason if customer not available during visit | From mobile, I have given the reason, but on the web it is showing as a date picker. The reason is not reflecting there. | Web
| pdf | data is not reflting in the pdf | Backend
kowtha team
|  | Search bar functionality missing – search bar present but not working | Web |  |  | fixed
|  | Branch location field & type of PD with manual entry should be present (Billing Module) | Web
|  | Add a filter for “Appointment Postponed” for segregating loans. | Web |  |  | fixed
|  | ARFA Fincap – Amount field missing in all Mobile/Web/Report | All
|  | Changes done in mobile are getting saved, Web changes not getting saved – showing “No pending changes” | Web |  |  | fixed
|  | ARKA – Work hours timer available for selection only once – required twice (start and end) or it can be given as a descriptive field. | Mobile
|  | Clicking “Photo Capture” shows document upload option – photo capture and doc upload should be separate - Only two photos can be uploaded per doc selection | Mobile
|  | Financial analysis – two columns (Actuals and Estimations) only for RBL/DCB; other templates need only Estimations, actuals are not required. | Backend
|  | Empty Excel sheet issue | Backend
|  | Net profile limit (10L) – testing ongoing | Backend
|  | Timestamp not in IST | Backend
|  | Timestamp must be on photo – formatting required (no colour banner) – (low priority) | Backend
check the whole process from initiation, field, backend, verifier, admin works and identify is there any issue - kowtha team need to be check yet
|  | if appointment postponed a notification to be popup. | Web
|  | pls give filter option to all fields in the loans page, verify page | Web |  |  | fixed
|  | I thin options in bank name; templet name are mismatched with each other in the web while initiating the pd. Check and discuss | Web
|  | pls give space to provide alternate number while initiating the case | Web | *
common points for all templets
|  | pls give space to provide alternate number while initiating the case (suggestion: add limit from 10 to 30 digits to the current mobiel number option) | Web&Mobile
|  | unable to edit autofilled fields in app, web | Web
|  | for discriptive fields like business synopsis, other observations, concerns, Strengths,Weaknesses, Assets ... etc - space in app and web to be bigger and when clicked on enter button a dot to be present indicationg the another point like synopsis option in fi web | Web
|  | pls remove the documents upload from photos capture. both are mixed up and unable to capture business photos seperatly. | Mobile
insert the documents upload option as discussed in the meeting
|  | when the photos are uploaded from gallery geo tag baner is not required. same for the photos taken through app with out geo tag | Backend
|  | insert the transperant baner ot remove the colour baner from geo tag on the potos. also adjust the gep tag to be appear on photo at bottom coener so that photo can be visible clearly. | Backend
|  | unble to add & download the photos in app, web | Web&Mobile
|  | in app & web there are some fields when we can enter only numeric digits. in those places either add the posibilty to enter speceial charectors (%, @, &, ₹, $....etc) or give it as discriptive where we are able to add any contents | Web&Mobile | *
|  | in all formats, all questionnaire has to be in bold format. so that we can diffebtiate questions and answers in the PDF. | Backend
|  | add seperate tab for postponed cases in app | Mobile | *
give option to add extra income/expence in the financial analysis. if the export excel sheet worked perfectly we can add in it. does the admin approval limit of 10 lakhs work in the exported excel sheet as a copy was downloaded seperatly
|  | each time when the details were saved the page is going to top | Web
|  | exporting the Excel gives an empty sheet but not the figurs we already filled in the web. | Backend
Synopsis, feed back, select templete options are nowhere usable in the web - please discuss with team
|  | in app for some formats large space given for business synopsis for some very little (space for single line) given. in web for all formats space to enter bysiness synopsi given very little. we have commented where we mention the business synopsis in "fields list excelsheet" for all formats. can we map the details entered in the app in those option to appear directly at "Synopsis" area available at the bottom of web and same tobe appear in the PDF where we need business synopsis. if this can be possible we may have solved the space gap issue in app & web and also synopsis option usage is done instead of removing it or keeping idealy (as synopsis submissing is failing in web) | Web&Mobile |  | Jeevan
|  | can we do the same for status of the case also which is available at the bottom of the web | Web
|  | unable to edit autofilled fields in app & web | Web
|  | pls remove the documents upload from photos capture. both are mixed up and unable to capture business photos seperatly. |  |  |  | Fixed
|  | time is not asper the indian time zone on the photos | Backend
|  | the date order has to be DD/MM/YYYY | Web |  |  | fixed
|  | unble to add & download the photos. | Web
use the kowtha letter head which are shared on 5/8/25 through mail from opspd@cakowtha.co.in
|  | increase the size of the letters/words in the generated pdf report | Backend
|  | adjust the borders, between questions in the left side and answers in the right side of the PDF, in a way that the answers to be clealry catched to the eye. at present the questions on the left of pdf are catched to the eye when we open a report. | Backend
|  | green tics not appearing and also save option not avaialbel in the app. but we are able to submit the case in app | Mobile |  | Jeevan
|  | for discriptive fields like business synopsis, other observations, concerns... etc - when clicked on enter button a dot to be present indicationg the another point like synopsis option in fi web | Web
|  | exporting the Excel gives an empty sheet but not the figurs we already filled in the web. | Backend
|  | Financial analysys given in the previous APK was bettter as it is calculating the grossprofit & net profit automatically by adding or removing the amounts. In this just the positions of grossprofit & net profit are to be below instead of at top (in the previous apk) | Mobile
|  | it is not seeking for admin approval if the net profit is over the specified limit. | Backend
|  | time format is still not as per the indian time zone. | Web
|  | failed to submit the synopsis in the web. Is this required just check with team as we mention the synopsis in the about the business place. | Web
Documents attachement & photos attchement was completely messed up.
|  | what ever you selct the templet format in the web at the end of verifiction report is genereated in the format which was selected at the time of initiation | Web
|  | page margins are going out of the page in the PDF when content is large. | Backend
|  | Documents Observed - can we make it to appear in points wise in the PDF. Or can we give the documents upload option here so that documents observed and file of observed douments can be done at the same time pls discuss. | Backend
status is appearing as filled in the details but not as per the option given at last in the web.
|  | as we are unable to submit the synopsis we have to check where those points appear in the PDF. | Web
|  | can we remove the outside boarder for photo as it is ocupying more space with out interupting the already geo tag; daie & time . Can we adjust the size of the photos. Or will it be possible to over lay the whole geo tag (lat&long; date&time; address) on the photo with out the colour baner so that we can adjust the more number of photos in single page with out inturupting any & also photo can be visible clearly.. - red marked is preferble as other options will rise audit qury in bank. | Backend
|  | if we select photo without geo tag still we are getting the baner which is blocking the some part of the photo. same is happening for photos uploaded from gallery also | Backend
|  | I cannot find re-edit option after submitting the report. | Web
|  | synopsis, status options in the web are not usble at any where in the PDF. So pls remove - discuss | Web | dis
ARKA FINCAP FORMAT
|  | Amount of Loan MISSING IN BOTH APP & WEB | Web&Mobile
|  | About the Applicant - NEED BIGGER SPACE IN APP & WEB | Web&Mobile |  |  | Fixed
|  | in the Family Members details - changes are not saving in the web. It is showing as "no changes to save" even we made some changes. | Web |  |  | fixed
|  | in the Banking Details - changes are not saving in the web. It is showing as "no changes to save" even we made some changes. | Web |  |  | Fixed
|  | in the Assets Details - changes are not saving in the web. It is showing as "no changes to save" even we made some changes. | Web |  |  | Fixed
|  | in the No. of Loans Details - changes are not saving in the web. It is showing as "no changes to save" even we made some changes. | Web |  |  | Fixed
|  | Business Summary - need bigger space in web | Web
|  | in the Name and Contact Number of Regular Customers Details - changes are not saving in the web. It is showing as "no changes to save" even we made some changes. | Web
|  | Business Activity and Stock Level observed at the time of visit - in the app it was given as discriptive but in the web it was given to select the time once. | Web
|  | Documents Observed - need bigger space in app & web | Web&Mobile |  |  | Fixed
|  | Concerns - need bigger space in app & web | Web&Mobile |  |  | Fixed
|  | Other Observations - need bigger space in app & web | Web&Mobile |  |  | Fixed
|  | change the financial analysis as discussed in the meeting. financial analysisi attched in the first apk testing file was good just Gross profit and net profit positions to be appear below the table intead of at top. | Web&Mobile
Business Activity and stock level observed at the time of visit - in the pdf report the web contants are appearing(i.e. Time ) not the app contents.
|  | Concerns - can we make it to appear in points wise in the PDF | Backend
|  | Other observations - can we make it to appear in points wise in the PDF | Backend
|  | Other incomes - can we make it to appear in points wise in the PDF | Backend
AXIS BANK FORMAT
Person Met - is the options ok check and discuss with team
|  | Any other observations / remarks during visit: - need bigger space in app & web | Web&Mobile |  |  | Fixed
|  | Business/Financial Profile - what are debit fields & credit fields in web | Web
|  | Is Resi Cum office? If yes details of separate office set up - check in app & web | Web&Mobile |  |  | Fixed
|  | Common Points applicable for all cases - numbering for all points in PDF is not necessery - discuss | Backend
|  | product - pls add EL & others options in app, web | Web&Mobile |  |  | Fixed
|  | Status of PD - pls add Credit refer intead of Credit manager visit needed in app & web | Web&Mobile |  |  | Fixed
|  | change the financial analysis as discussed in the meeting. financial analysisi attched in the first apk testing file was good just Gross profit and net profit positions to be appear below the table intead of at top. | Web&Mobile
|  | ANNEXURE1: Income assessment for Asha Home Loans - complete table missing in app | Mobile |  | Sandeep
|  | PD Officer Name: - missing in app, web, pdf | All
|  | PD Officer Signature - missing in app, web, pdf | All
|  | Business Model & Background of Business - need bigger space in web as this is business synopsis area | Web
|  | failed to submit the synopsis in the web. Is this required just check with team as we mention the synopsis in the about the business place. | Web
|  | pls add both initiated address & visited address in app & web & PDF instead of "full address" | All
|  | details save option in web not working propely in web. some times the changes made are not saving even though 'changes saved successfullu' popup appeard | Web
|  | Family Background - all the details filled in app & web are not appearing in PDF - will it be better if given in the tabular form discuss | Backend
|  | Nature of Business (Other) - not appearing in PDF | Backend
|  | at present all the details filled are appearing in the paragraph form instead of points wise. | Web
|  | Top 3 clients (customers) - add another option for "Average debtor days" | Web&Mobile |  |  | Fixed
|  | Top 3 clients (suppliers) - add another option for "Average creditor days" | Web&Mobile |  |  | Fixed
|  | in the PDF mobile number is taking as average debtor/creditor days like Varna - 08522450541 days ; kishore - 8898987895 days ; | Backend
|  | If yes, established through document - missing in PDF | Backend
|  | Any cheque bounces seen (Y/N) - answer not populating in PDF | Backend
|  | Agency Name & Seal, Geo Tagging & Photographs of business premises : move the both positions to last after the annexure & disclimer cluase. | Backend
|  | annexre is generating in the PDF but not available in app & web so amounts are not generating in pdf. only empty table appearing | Backend
TATA UBL
|  | in 'repayment from' option "bank name" is autofilled as per the initiated bank name but it is the name of the bank from which the applicant wants to pay the EMI to this loan - pls give it as discriptive in app, web instead of auto filling | Mobile
|  | banking details given for one, adding another bank details is not available | Mobile
|  | in sales & profit details change the optins Turnover (FY 2024 2025), Exp. Turnover (FY 2025 2026) as previous financial year turnover & Expected turnover in this years - in next year we have to change the years as 2025 2026; 2026 2027 and keepdoing early by changing it as i suggested wont require early modifications | All
|  | Utilitybill(ClearPhototobeTaken)last2months& present month units consumption to be written - pls add this as per format in app [option is under Value Added Information in format] | Mobile
|  | questionery from 28.Pan Card to 35. lat long in format are missing in app & web | Web&Mobile
|  | Acknowledgment of Site Visit - total missing in app & web. generating in PDF but unable to to fill answers in it as not available in app & web | Web&Mobile
|  | auto filled ansers are not generating in the PDF. | Backend
|  | Name of Co-Applicant(s) - in the PDF "(wife)" appearing next to the answer. | Backend
|  | Sr. No & Particular Head - pls keep all questions in bold format | Web&Mobile
|  | Residential Address - Address is not generating in the PDF. | Backend
|  | Current Business Details - need bigger space in web and synopsis has to be in poins wise intead of paragraph | Web
|  | Third Party Confirmation - in the PDF the answer is not generationg what we filled in app or web. it is always generating ""Got years positive response about the applicant"" | Web&Mobile
|  | Document Seen - missing in PDF | Backend
|  | while entering the new details in web its showing that no changes occured and its not saving the report. | Web
|  | in the web buzz details tab should be go bigger and should provide bullet points as it was business synopysis. | Web
|  | Repayment from - (Bank name, Type,Account No) options not available in the web. | Web
|  | In the sub group of web Address of PD and persona met spell was wrongly done | Backend
|  | In Value added information, sub group of stregths and weakness need bigger space to enter description in bullet paragraphs | Mobile
|  | change the financial analysis as discussed in the meeting. financial analysisi attched in the first apk testing file was good just Gross profit and net profit positions to be appear below the table intead of at top. | Web
RBL-LIP
|  | In the APP we have observed in the Type of borrower options has givne for entity whereas it should be draft as individual concerns | Mobile
|  | green tics not appearing and also save option not avaialbel in the app. but we are able to submit the case in app | Mobile
|  | Shop Address - not autopopulated in app, web & PDF and also unble to edit in app, web | All
|  | in the app, buzz deatils and sub of shop address was not highlighted and we are unable to do manually adn which it was not auto populated from the initiation task | Web&Mobile
|  | In the app,Documents Observed point is disclaimed as options which to be corrected and given as writtern with bullet points while we do enter | Mobile
|  | In the app we have observed in the Type of borrower options has givne for entity whereas it should be draft as individual concerns | Mobile
|  | Own contribution, Particulars, Remarks - these three options are duplicated in app & web. please remove them appearing under "applicant's main banking details". | Web&Mobile
|  | In the app, Loan deatils -Own contribution- theme should be deleted, which it was duplicated below also | Mobile
|  | In the App, Latitudes and longitudes should be auto populated which was missed in the APP, same is cross checked with the web an found same thing was missed | Mobile
|  | In the web, date format should be day/month/ year, whereas it was showing month and year which was US format | Web
|  | family details - About Applicant; About Co-applicant; their family details has to be inseperate points. but in the PDF all are generating in single line | Backend
|  | PF/ESI Applied - answer not generating in PDF | Backend
|  | Latitude, Longitude - options are not available in app, web. so not autopopulated in PDF. | All
|  | Field Visit Time; PD Verified By (Officer); PD Verified Date - these three options appearing in the PDF below the photos, but there are not in the originally given format/templete. | Backend
|  | income assesment details and balence sheet details are mixed up in the web. also debit side fields are not available in the web. please reove the balance sheet fields from both app and web and attache the financial statement only which was specifically shared for RBL format at time when all templetes are shared via mail. | All
Axis Finance
|  | axis finance-hl format is not opeing in app. it is saying as something went wrong, undefined is not finction | Mobile
hero housing - self employed
|  | autopopulated answers like application number, applicant name...... etc are not populated in app, web & PDF and also not able to edit | All
|  | PD Visit date and time - both options duplicated in app & web | Web&Mobile
|  | Lat log of business address - these options are appeared multiple times in app & web | All
|  | Borrower details - duplicated in app & web | Web&Mobile
|  | Family details - appeared multiple times in app & web | Web&Mobile
|  | family background notes; number of dependents - these options available in app&web but not in original templete/format | Web&Mobile
|  | business Name - duplicated in app & web | Web&Mobile
|  | No of total suppliers and details of terms for credit period - in app & web pls give this as discriptive so that we can add both numeric and alphabets | Web&Mobile
|  | No of total customers and details of terms for credit period - in app & web pls give this as discriptive so that we can add both numeric and alphabets | Web&Mobile
|  | supporing documents collected - these options available in app but not in original templete/format | Mobile
|  | Income assessment details - pls add Travelling & Transportation, Repairs & Maintanance options also along with rent, electricity.....etc or give option to add extraincomes/expences, what ever the name of expence/income and amount | Web&Mobile
Income assessment details(Income assessment line items) - there is option to add Particular;Amount (Rs.) Monthly;Comments in app and web but ther are nowhere appearing in PDF. please disciss with team is these options necessery.
|  | there is no option to add comments for all options in income calculation table(sales, purchase, other income... etc) except for Net monthly income coomments, obligations coomments, Net residual income coomments | Web&Mobile
Reason if customer not available during visit - this is an extra option available in both app & web but not in PDF. also in the web it was given as to select the date instead of populating the answer filled in app. shall we keep this option or remove once discuss with team.
|  | PD visit time - in the app it was given as discriptive but in the web it was given to selct the time. dispritive answer in app is also not populating in web. | Web
|  | Latitude of business address; Longitude of business address - theser are not autopopulating in app & web. instead we have to enter manually. | Web&Mobile
|  | No. of dependants - this is an extra option available in both app & web but not in PDF. shall we keep this option or remove once discuss with team. | Web&Mobile
Family background notes - this is an extra option available in both app & web but not in PDF. shall we keep this option or remove once discuss with team.
|  | there are somany questions duplicated in app & web with tiled (legacy) | Web&Mobile
|  | Turnover of last three years and current year till date (Total actual turnover of customer) - in the web it was given as to select the date instead of populating the answer filled in app | Mobile
|  | Total debtors and creditors as on date (mention defaults/write offs) - in the web it was given as to select the date instead of populating the answer filled in app | Web
|  | Whether customer visited the property - in the web it was given as to select the date instead of populating the answer filled in app | Web
|  | Property is occupied by whom and reason if not self-occupied - in the web it was given as to select the date instead of populating the answer filled in app | Web
|  | When seller bought the property - in the web it was given as to select the time instead of populating the answer filled in app | Web
|  | each time when the details were saved the page is going to top. repeatedly happen in this format | Web
|  | Supporting documents collected - this is an extra option available in both app, web & PDF. shall we keep this option or remove once discuss with team. | All
|  | the questions also appear at the right side of the PDF along with the answers. shall we keep or remove pls discuss with team. this happening from Current business details to the last question Final PD status. can we remove the questions in the right side of the pdf and position the answers to adjecent to that respective question in the left side of the pdf | Backend
|  | Size / area of business premises - answer not generating in PDF. | Backend
|  | Details of supplier and customer - all question & answers and added supplier/customer details (along with Name, business name, relation, contact ) are not generating in PDF. instead it is appearing as "not provided" even though we have added somany details. | Backend
|  | Field Visit Time; PD Verified By (Officer); PD Verified Date - these three options appearing in the PDF below the photos, but there are not in the originally given format/templete. | Backend
|  | remove the financial analysis as same is available in tabuala form in PDF (or) change the financial analysis as discussed in the meeting. financial analysisi attched in the first apk testing file was good just Gross profit and net profit positions to be appear below the table intead of at top. | Backend

## mobile bugs
S.No. |  | Bugs Identified |  | resources | BYS Status | Developer Remarks | Kowtha Status | Kowtha Remarks
1 | aditya birla | The Partners/Management contact number field should be of integer type, but it is currently showing as string. | frontend | jayakrishna | Completed
|  | The PAN field is also present, and validation for the PAN number should be applied. | frontend | jayakrishna
| family members | The Family Member → Age field needs to be of integer type. | frontend | jayakrishna | Completed
| bank details | The Banking Details is a heading, but in the mobile app, it is showing as an input field. | frontend | jayakrishna
| image loarding | While trying to upload the image, it is loading continuously in all places. | frontend | jayakrishna
| image uploard | remove limition to uploard the images |  |  | Completed | selecting with gallary then also in the image geo tag is reflucting
AMBIT
|  | pd initiated address should not be editable | frontend | jayakrishna | Completed
| family details | The Education field needs to have a dropdown. | frontend |  | Completed
|  | The Purpose of Loan field should not be editable. | frontend |  | fixed
|  | In the Name / Contact Number of Regular Suppliers section, the Add button should include options for Customer and Supplier, but currently there is no option to enter customer details. | frontend | jayakrishna
| banking details | When I click on the Banking Details field, an error message appears saying “Something went wrong.” | frontend | jayakrishna | fixed
AXIS FINANCE
| applicant asked to postpone | When I click on the Applicant asked to postpone? field and select the No option, an error message appears saying “Something went wrong.” | frontend | jayakrishna | fixed
| postpone | While trying to postpone by setting the date and reason, after clicking the Submit button, an error message appears saying “Department is query params.” | frontend | jayakrishna | fixed
AXIS FINANCE UBL ABOVE 10L
| basic details->appointment fixed | The Appointment Fixed field should have a time picker, but it is currently showing as a string input. | frontend | jayakrishna | fixed
|  | The No. of Visits field should be of integer type. | frontend | jayakrishna | fixed
| family details | The Qualification field should be a dropdown. | frontend | jayakrishna | fixed
| suppliers/ creditors | The No. of Fixed Suppliers, Credit Period, and Cash/Cheque Proportion fields need to be in integer format, but they are currently taking string values. | frontend | jayakrishna | fixed
| expenditure-salaries nd wages | The No. of Employees field should be of integer type. | frontend | jayakrishna | fixed
|  | The No. of Labours input field should be of integer type. | frontend | jayakrishna | fixed
| axis finance ubl above 10L | In the Asset Details → Car/Bike field, there is no option to enter the data. | frontend | jayakrishna | fixed
| bank details | The Open Since field should be of integer type. | frontend | jayakrishna | fixed
| third party check | The Site Coordination field should not be editable. | frontend | jayakrishna | fixed
| observations | There is no option available to enter the details. | frontend | jayakrishna | fixed
|  | In the document, the Financial Summary and Recommendation sections are not present, but they are displayed in the mobile app. | frontend | jayakrishna | fixed
|  | The “Area measured” field should be of number (int or float) type — not string — | frontend | jayakrishna | fixed
AXIS FINANCE UBL below 10L
|  | The Initiated Address field should not be editable. | frontend | jayakrishna | fixed
| basic details->appointment fixed | The Appointment Fixed field should have a time picker, but it is currently showing as a string input. | frontend | jayakrishna | fixed
| basic detals | The No. of Visits field should be of integer type. | frontend | jayakrishna | fixed
| bank details | The Open Since field should be of integer type. | frontend | jayakrishna | fixed
| third party check | site coordination feild should not editThe Site Coordination field should not be editable. | frontend | jayakrishna | fixed
| references | The Contact No field should be of integer type. | frontend | jayakrishna | fixed
| knowing since | int | frontend | jayakrishna | fixed
| asset details->area measured | The “Area measured” field should be of number (int or float) type — not string — | frontend | jayakrishna | fixed
| purchase year | int | frontend | jayakrishna | fixed
|  | In the Family Members Details section, the Dependent field needs to have a dropdown with options Yes and No. | frontend | jayakrishna | fixed
| suppliers/ creditors | The No. of Fixed Suppliers, Credit Period, and Cash/Cheque Proportion fields need to be in integer format, but they are currently taking string values. | frontend | jayakrishna | fixed
|  | The Average Stock Maintained field should be of integer type. | frontend | jayakrishna | fixed
|  | The Turnover and Margins fields should be of integer type. | frontend | jayakrishna | fixed
| axis bank |  |  | jayakrishna
| family details | The Qualification field should be a dropdown. | frontend | jayakrishna | Pending
|  | In the Family Members Details section, the Dependent field needs to have a dropdown with options Yes and No. | frontend | jayakrishna | Pending
| other details observed | business name board seen input feild text is refluting as black clour it should be light grey | frontend | jayakrishna | Pending
| pd address type | in the input field ther text is reflucting as select an option is in black colour it should be light grey colour |  |  | Pending
| common points applicable for all cases | The Turnover and Margin fields should be of integer type (int), not string, |  |  | Pending
|  | The Peak Sales Months Volume should be in INR and of integer type. |  |  | Pending
|  | The low Sales Months Volume should be in INR and of integer type. |  |  | Pending
axis agri
|  | name of firm is not populating in the mobile app |  |  | Pending
|  | Address of the Firm not populating in the mobile |  |  | Pending
|  | Name of Person Met field the feild executive user name is populating in the mobile |  |  | Pending
|  | Date & Time of PD field need to have date and time picker |  |  | Pending
Documents Provided during Visit: not having on the in mobile
Business License Related Information: not having in the mobile
Other Businesses owned if any & other Incomes:
End use of the Loan & Loan amount Required
annual turnover is not having in the doc but we are showing in the mobile app
Any other Loan Obligations of the Firm doc but in the mobile the text is showing as other Loan Obligations of the Firm
not able to submit the axis agri bank errror message is reflucting
arka fincap
| regular customer | name and contact number of regular customer->contact no field it should be int
| regular supplier | name and contact number of regular suppliers->contact no field it should be int
net margin field should be int
| status | need to have dropdown
chola
loan requested field the loan amount should be refluct
family details -> relationship field dropdown need to refluct
| pdf | in the pdf ->asset/customers reference/other income/existing loans/banking details/comfort factor/discomfort / are not reflucting in the pdf
DCB
name is not populating in the mobile
business address should not be editable in the mobile
| Details of Directors & Proprietor | In the Details of Directors & Proprietor section, there is no option to enter the details, and the fields are already added in the Borrower’s Name form.
| Details of ALL Loans as on | Details of ALL Loans as on field there is no option to enter the details
| personal assets of proprietor | personal assets of proprietor ther is no option to enter the details
| 4) Details of Customers / Clients: Not Applicable- Walk in Customers. | Details of Customers / Clients: Not Applicable- Walk in Customers. no option to enter the details
| 4) Details of Suppliers: | Details of Suppliers: no option to enter the details
| 4) Sister Companies | Sister Companies no option to enter the details
| 4) Insurance Details | 7) Insurance Details no option to enter the details
Insurance Company Name: - no option to enter the details
loan requested field the loan amount should be refluct
comprehensive actuals vs estimated analysis field is not havig in the doc but in the mobile we are showingg
not able to submit the dcb template in the mobile error message is refluting as frontend validation error
HERO FINCORP
name of the concern is is lock not able to give the details
phone number field should have int
The Appointment Fixed field should have a time picker, but it is currently showing as a string input.
loan amount should not editable
family details -> relationship field dropdown need to refluct
age field need to have int
qualification field need to have dropdown
| About the Business: | About the Business: there is no option to enter the details
| financial summery | net margin field should be int
| Customers /purchases | contact number should be int
| existing loan | existing loan is no option to enter the details
| detailed financial analysis with balance sheet | detailed financial analysis with balance sheet is not having in the doc but we are showing in the mobile app
herohousing salaried
loan account no is not ppopulating in mobile
name os customer is not populating
pd visit date field should be date picker
pd visit time field should be time picker
pd address field business address is populating snd it should not be editable
loan amount should not editable
family details -> relationship field dropdown need to refluct
family details -> qualifaction field dropdown need to refluct
current bussiness name should not be edit able
latitude and longitude of office address pd aaddress name is populating
| fields | The fields in the document and the mobile app are not matching.
| investment and properties | need add separate fields not haveing in the doc but in mobile it is showing
| existing loan | need to remove it is extra fied not haveing in the doc but in mobile it is showing
| loan purpose | need to remove it is extra fied it is not haveing in the doc but in mobile it is showing
| environmental and social safe guards | need to remove it is extra fied it is not haveing in the doc but in mobile it is showing
| Latitude & Longitude of office address | On mobile, the Latitude & Longitude of the Office Address field are populating the same as the PD Address.
herohousing self employed
loan account no is not ppopulating in mobile
name of customer is not populating in the mobile
pd visit time field should be time picker
The PD Visit Date and Time (legacy field) is already being shown as PD Visit Time, but again another field is appearing as PD Visit Date and Time, causing duplication.
in the doc log/lat of business address but in the mobile show as extra fieds
in the pdf some places data os not reflucting
kowtha team
Save option not available, green tick not coming but all the details are getting submitted at the end
Fields auto-filled from mail also should be editable

## Change log
S.No. | Item Description | BYS Status | Developer Remarks | Kowtha Status | Kowtha Remarks
1 | Single app to serve both FI and PD flows as there are shared users between the two | Done
2 | Redirect users directly to PD flow without requiring logout | Done
3 | AI should auto-extract fields from emails using the 24 templates shared by Kowtha
4 | FE should be able to choose the email template for field extraction
5 | Manual entry should be available for fields not covered by auto-extraction
6 | Profit/Loss (P/L) calculations to be auto-generated within the app | Done
7 | Knowledge transfer on P/L calculations needed from Kowtha team (2nd week of August) | Done
8 | P/L results should be editable by Admin, Backend, and Verifier (only with Admin approval) | Done
9 | Details filled by FE must be reviewed by Verifier (no admin approval needed)
10 | Storyboard to be handled by backend; app will not manage storyboarding
11 | Define and manage roles: Admin, Verifier, FE, Backend/Ops, and Follow-up | Done
12 | AI should read mail content and pre-fill form fields; FE can edit them | Done
13 | FE should be able to add notes and upload attachments per case
14 | Feature to re-assign a case to another FE or team member | Done
15 | Enable follow-up tracking to monitor FE task status and eliminate manual tracking
16 | Excel upload option not needed if report format is finalized as PDF | Done
17 | Check availability of app tracking tools under a free tier | Done
18 | FE to have Start/Stop buttons in app to track distance traveled (in kms) | Add on
19 | Attendance tracking: login time should be between 9–9:30 AM; feasibility of admin module to be checked
20 | App should generate Excel reports on daily case count for billing purposes | Add on
21 | Ability to count number of cases with Backend and Verified statuses
22 | Add a field to record internal reasons for case rejections (not related to bank rejections) | Add on
23 | List of mandatory documents should be displayed; FE marks received docs as collected
24 | Remove End button in tracking section, Submit should end the tracking | Done
25 | Add a new 'Instructions to FE' field inside the case - no character limit | Done
26 | No separate 'Follow-up' role, Followup team will be give Initiator role | Done
28 | if any Appointment issue, should be available in the notification TAB
29 | feasibility to change/edit the Backend & verifiers names at any time and prefillied details also at verification stage at any time. | Can be done
30 | increase the PD photos capture limt to 50, also adjust the time stap appearence on the photo and gap between photos in the report - reference images sent | Done
31 | request tracking log | BYS to share when required
32 | dash board to all web users (initiator, verifier, admin) | Done
33 | Admin approval for net profit more than 10L | Can be done
34 | When we put the cursor on the page it should show in which stage is the case (assigned/fv completed/completed) | can be done
35 | Name of the bank should be displayed in the dashboard | can be done
36 | PD/LIP case type should be displayed in the dashboard | Billing Module related